## velam
Date	Feature branch name	Functionality	Problem	status	solution
01/09/23	Feature-signup-page-velam (login feature)
01/10/23	1.Feature-signup-page-velam / 2.feature-signin-page-velam(signup feature)		1.Empty Input field – creating null token and storing in the local storage. / 2.if the email and password is not valid / incorrect – storing null token in local storage / 3.due to above 2 reason , at backend jwt malformed error and front end login function is not working	solved	1. check the user inputs and don’t accept null input / 2.check the token from back end , if it is null don’t store in the local storage.
01/11/23	1.Feature-profile-page-velam
01/12/23

## ahmet
nav